## Instructions
DBEDC — DAILY ROAD MAINTENANCE MONITORING FORMAT
Dhaka Bypass Expressway (N-105), Handed-Over & Opened Section: K-4+000 to K-22+000
PURPOSE
This workbook is the single standard format for the QC Department to (a) log every road-condition/maintenance defect found on the opened K4–K22 stretch, (b) track each defect through to repair and verified close-out, and (c) compile the daily report submitted to the CEO. Use the same workbook every day — do not create a new file per day.
HOW TO USE — DAILY ROUTINE
1. Site inspection: Walk/drive the K4–K22 stretch (rotate sub-sections so the full length is covered at least once every few days, with high-risk locations checked daily).
2. Log new defects: For every new observation, add one row in the 'Defect_Register' sheet — fill only the yellow cells; Days Open, Overdue and IDs are automatic.
3. Update existing defects: When a logged defect is repaired, go to its row in 'Defect_Register' and update Status, Date Repaired and (after your own re-inspection confirms it) Date Verified/Closed. Never delete a closed row — it is the record that the defect was fixed.
4. Fill today's row in 'Daily_Report': one row per calendar day. New/Repaired counts and the cumulative open-defect count pull automatically from the register; add your narrative in 'Key Observations' and 'Follow-up Action Required'.
5. Check 'Dashboard' for the day's summary (open/closed/overdue/critical counts) before sending the report to the CEO — this sheet is what you paste into or attach with the CEO email/briefing.
COLOUR LEGEND
Yellow fill = type here (manual entry).
White/blue-header cells = automatic formulas. Do not overwrite.
Green fill (Defect_Register Status column) = defect verified closed.
NOTE ON EXAMPLE ROWS
Row 4 of 'Daily_Report' and rows 4-6 of 'Defect_Register' are sample entries showing the expected format and realistic content — overwrite/delete them once real data collection begins, or keep them as a reference at the bottom of the log.

## Dashboard
DBEDC — MAINTENANCE MONITORING DASHBOARD ¦ K-4+000 to K-22+000 (auto-updates from Defect_Register)
As of: | 2026-09-05
DEFECT STATUS SUMMARY |  | OPEN DEFECTS BY SEVERITY
Total Defects Logged | 71 | Critical - Safety Hazard | 2
Open | 71 | Major | 3
In Progress | 0 | Moderate | 63
Repaired - Pending Verification | 0 | Minor | 3
Verified - Closed | 0
Reopened | 0
Overdue (past target repair date) | 0
TODAY'S ACTIVITY (from Daily_Report, last filled row)
Latest Report Date | 2026-09-02
New Defects (latest day) | 44
Repaired & Verified (latest day) | 0
Cumulative Open (latest day) | 71

## Daily_Report
DBEDC — DAILY ROAD MAINTENANCE MONITORING REPORT ¦ Section: K-4+000 to K-22+000, N-105 Dhaka Bypass Expressway
Date | Day | Weather | Chainage From (Km) | Chainage To (Km) | Inspection Team | Traffic Condition Observed | Overall Pavement Condition | New Defects Today | Repaired & Verified Today | Cumulative Open Defects | Key Observations / Day's Development | Follow-up Action Required | Reported to CEO (Time/Mode) | Report Prepared By
2026-09-01 | Saturday | Light rain | 4+000 | 5+300 |  | Heavy - morning peak congestion near K-9 | Fair | 27 | 0 | 27 |  |  | 09:15 - Email + WhatsApp brief
2026-09-02 | Sunday | Light rain | 5+300 | 7+700 |  | Moderate | Fair | 44 | 0 | 71 |  |  | 09:00 - Email
[6 empty] | Heavy - morning peak | Fair to Good | [5 empty] | 09:10 - Email + WhatsApp brief

## Defect_Register
DBEDC — DEFECT & MAINTENANCE REGISTER (MASTER LOG) ¦ Section: K-4+000 to K-22+000, N-105 Dhaka Bypass Expressway
SL/Defect ID | Date Identified | Chainage (Km) | Location / Carriageway | Defect Category | Severity | Description / Extent | Photo Ref. | Identified By | Responsible Party | Recommended Action | Date Notified | Target Repair Date | Status | Date Repaired | Date Verified / Closed | Days Open | Overdue | Remarks / Follow-up
1 | 2026-09-01 | K4+100 to 4+320 | Main Carriageway - L | Damage/Cut | Moderate | Isolation barrier cutting /damage by local people | IMG-0281 | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
2 | 2026-09-01 | K4+100 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people | IMG-0265 | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
3 | 2026-09-01 | K4+120 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people | IMG-0298 | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
4 | 2026-09-01 | K4+180 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people | IMG-0299 | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
5 | 2026-09-01 | K4+250 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people | IMG-0300 | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
6 | 2026-09-01 | K4+280 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
7 | 2026-09-01 | K4+290 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
8 | 2026-09-01 | K4+300 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib | O&M Contractor | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
9 | 2026-09-01 | K4+330 | Median | Damage/missing | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Installation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
10 | 2026-09-01 | K4+330 to K4+370 | Median | Damage/missing | Moderate | Central median delineator missing |  | SE: Prodip - Habib |  | Installation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
11 | 2026-09-01 | K4+330 to K4+370 | Median | Damage/missing | Moderate | Central median drainage pipe is clogged with sand and grass. |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
12 | 2026-09-01 | K4+580 | Median | Damage/missing | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Installation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
13 | 2026-09-01 | K4+610 to K4+620 | Median | Damage/missing | Moderate | Central median anti- glare panel board damage/ missing, delineator missing, drainage pipe is logged with sand and grass. |  | SE: Prodip - Habib |  | Rectification and Installation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
14 | 2026-09-01 | K4+650 to K4+800 | Median | Damage/missing | Moderate | Central median anti- glare panel board damage/ missing, delineator missing, drainage pipe is logged with sand and grass. |  | SE: Prodip - Habib |  | Rectification and Installation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
15 | 2026-09-01 | K4+630 to K4+700 | Median | Damage/missing | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
16 | 2026-09-01 | K4+890 | Median | Damage/missing | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
17 | 2026-09-01 | K4+900 | Guardrail/Barrier | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
18 | 2026-09-01 | K4+920 to K5+000 | Service Road - Left | Guardrail/Crash Barrier Damage | Major | W-beam Guard Rail Damaged |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
19 | 2026-09-01 | K5+020 | Road Marking | Faded/Damaged Road Marking | Minor | Road Marking Paint Damaged |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
20 | 2026-09-01 | K5+050 to K5+070 | Guardrail/Barrier | Guardrail/Crash Barrier Damage | Critical - Safety Hazard | W-beam Guard Rail Damaged |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
21 | 2026-09-01 | K5+100 to K5+500 | Main Carriageway - L |  | Moderate | Grass at the road edge. |  | SE: Prodip - Habib |  | Remove grass and clean the road edge. | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
22 | 2026-09-01 | K5+130 to K5+160 | Median | Median/Landscape Damage | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
23 | 2026-09-01 | K5+130 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
24 | 2026-09-01 | K5+260 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
25 | 2026-09-01 | K5+260 | Median | Median/Landscape Damage | Moderate | Central median Anti-Glare Panel damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
26 | 2026-09-01 | K5+300 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
27 | 2026-09-01 | K5+400 | Median | Median/Landscape Damage | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-02 | 2026-09-10 | Open |  |  | 4 | On Track
28 | 2026-09-02 | k5+350 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
29 | 2026-09-02 | k5+380 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
30 | 2026-09-02 | k5+380 to K5+450 | Main Carriageway - L |  | Moderate | Grass on Road edge |  | SE: Prodip - Habib |  | Remove grass and clean the road edge. | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
31 | 2026-09-02 | k5+400 to K5+ 440 | Median | Median/Landscape Damage | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
32 | 2026-09-02 | k5+450 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
33 | 2026-09-02 | k5+520 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
34 | 2026-09-02 | k5+700 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
35 | 2026-09-02 | k5+700 to K5+720 | Median | Median/Landscape Damage | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
36 | 2026-09-02 | k5+780 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
37 | 2026-09-02 | k5+600 to K5+800 | Service Road - Left | Bush/plant/grass | Moderate | Grass and trees between the TR and SR. |  | SE: Prodip - Habib |  | Remove the grass and trees and clean the area. | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
38 | 2026-09-02 | k5+800 to 6+000 | Main Carriageway - L |  | Moderate | Grass on Road edge |  | SE: Prodip - Habib |  | Remove grass and clean the road edge. | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
39 | 2026-09-02 | k5+950 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
40 | 2026-09-02 | k5+930 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
41 | 2026-09-02 | K6+000 | Median | Guardrail/Crash Barrier Damage | Minor | Central Median New Jersey Barrier Damage |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
42 | 2026-09-02 | K6+010 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
43 | 2026-09-02 | K6+010 to K6+030 | Service Road - Left |  | Major | Grass and trees between the TR and SR. |  | SE: Prodip - Habib |  | Remove the grass and trees and clean the area. | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
44 | 2026-09-02 | K6+040 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
45 | 2026-09-02 | K6+080 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
46 | 2026-09-02 | K6+090 to K6+120 | Median | Anti glare panel board | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
47 | 2026-09-02 | K6+120 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
48 | 2026-09-02 | K6+140 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
49 | 2026-09-02 | K6+190 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
50 | 2026-09-02 | K6+210 to K6+220 | Main Carriageway - L | Anti glare panel board | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
51 | 2026-09-02 | K6+260 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
52 | 2026-09-02 | K6+300 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
53 | 2026-09-02 | K6+400 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
54 | 2026-09-02 | K6+600 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
55 | 2026-09-02 | K6+500 to K6+700 | Median | Safety | Major | Central Median Warning and Reflection Light Missing. |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
56 | 2026-09-02 | K6+700 | Main Carriageway - L | Guardrail/Crash Barrier Damage | Critical - Safety Hazard | W-beam Guard Rail Damaged by vehicle accedent |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
57 | 2026-09-02 | K6+700 | Main Carriageway - L | Anti glare panel board | Moderate | Central median anti- glare panel board damage/ missing |  | SE: Prodip - Habib |  | Istallation Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
58 | 2026-09-02 | K7+010 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
59 | 2026-09-02 | K7+020 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
60 | 2026-09-02 | K7+030 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
61 | 2026-09-02 | K7+050 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
62 | 2026-09-02 | K7+080 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
63 | 2026-09-02 | K7+100 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
64 | 2026-09-02 | K7+050 to K7+500 | Main Carriageway - L |  | Moderate | Grass on Road edge |  | SE: Prodip - Habib |  | Remove grass and clean the road edge. | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
65 | 2026-09-02 | K7+200 | Median |  | Minor | W-Beam Moveable Middle Barrier Bottom Surface Grass Plant |  | SE: Prodip - Habib |  | Remove grass is required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
66 | 2026-09-02 | K7+350 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
67 | 2026-09-02 | K7+380 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
68 | 2026-09-02 | K7+450 | Main Carriageway - L | Broken/damage | Moderate | W-beam Guard Rail Damaged |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
69 | 2026-09-02 | K7+520 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
70 | 2026-09-02 | K7+550 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
71 | 2026-09-02 | K7+560 to K7+700 | Main Carriageway - L | Isolation Barrier | Moderate | Isolation barrier cutting /damage by local people |  | SE: Prodip - Habib |  | Rectification Required | 2026-09-03 | 2026-09-11 | Open |  |  | 3 | On Track
Formulas:
Days Open = IF([Date Identified]="","",IF(AND([Status]="Verified - Closed",[Date Verified / Closed]<>""),[Date Verified / Closed]-[Date Identified],TODAY()-[Date Identified]))
Overdue = IF([Date Identified]="","",IF([Status]="Verified - Closed","No",IF(AND([Target Repair Date]<>"",TODAY()>[Target Repair Date]),"YES - OVERDUE","On Track")))